## Sheet1
| Year 2 | [7 empty] | Year 3 | [11 empty] | Year 4 | [12 empty] | Year 5 | [11 empty] | Year 6 | [11 empty] | Year 7 | [11 empty] | Year 8
 | time axis 2020-01-01 to 2026-09-01
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81
Role | 2023-07-01: Cyber School
| DI Jt User | [10 empty] | Space Dir | [12 empty] | DI Jt User
PGR Requirements | 2022-08-01: Interim / Transfer Thesis Submission; 2022-12-01: Interim Progress review 3 Submission; 2024-11-01: Interim Progress review 4 Intention to submit; 2025-05-01: Intention to Submit; 2025-08-01: Submission
Thesis | 2021-12-01: Interim Thesis Development; 2022-07-01: Interim Thesis Write up; 2022-11-01: Thesis Write Up; 2025-03-01: Submission
Conference Papers Presentations | 2022-02-01: Short Paper Present EHF 2022; 2022-04-01: Dstl AI2 Programme Present; 2022-12-01: HICSS Paper Present; 2023-05-01: Present AAMAS; 2024-08-01: Journal Submission
Journal Article Development | 2022-08-01: Conference Paper - AAMAS - Development of a Human Agent Cognition Model: A Review of Failures when adopting automation; 2024-03-01: Jounal Article Development of an Agent Human Cognition Model 2
Paper Development | 2021-11-01: Short Paper EHF 2022 Write Up; 2022-03-01: HICSS Paper Write Up; 2022-08-01: HICSS Paper Correction
Block Activities - The Plan | 2020-01-01: MODREC; 2020-12-01: Experimentation 1; 2022-08-01: Developing a Human Agent Cognition Model
[12 empty] | Transcription. Write up. Qualitiative ananlysis of results | [23 empty] | Designing the Experiment for Human Agent Cognition Models - University Setting | [6 empty] | Experimentatiin
[39 empty] | Ethical Approval | [6 empty] | Transcription - Write - Up and Review of results